## Fall 2016 Tentative Schedule
| Week # | Date | Sprint Day # | Meeting Room | Tasks
0 | 1 | 2017-01-09 | 1 |  | Preparation Tasks (see welcome post and the Task Desciptions tab); Sync Your LinkedIn Account;
|  | 2017-01-10 | 2 | In Person/Online | Learn the existing project; Read the documents; Watch the videos; Play with the existing software solution; Rank Proposed Projects; Accept Project Assignment;
|  | 2017-01-11 | 3 | In Person/Online | Collect User Stories; Create Project Backlog;
|  | 2017-01-12 | 4 | In Person/Online | Initial Requirement Analysis; Initial Feasibility Study; Initial System Design; all to be reflected in the Project Documentation file and be refined over time.
|  | 2017-01-13 | 5 | In Person/Online | Setup Development Environment; Initial Project Plan; Sprint Planning; to be reflected in the Project Documentation file and be refined over time.
1 | 2 | 2017-01-16 | 1 | Holiday | Martin Luther King Holiday (University Closed)
|  | 2017-01-17 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-18 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-19 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-20 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 3 | 2017-01-23 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-24 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-25 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-26 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-27 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
2 | 4 | 2017-01-30 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-01-31 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-01 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-02 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-03 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 5 | 2017-02-06 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-07 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-08 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-09 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-10 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
3 | 6 | 2017-02-13 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-14 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-15 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-16 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-17 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 7 | 2017-02-20 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-21 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-22 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-23 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-24 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
4 | 8 | 2017-02-27 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-02-28 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-01 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-02 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-03 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 9 | 2017-03-06 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-07 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-08 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-09 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-10 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
5 | 10 | 2017-03-13 | 1 | Holiday | Spring Break (University Open, No Classes)
|  | 2017-03-14 | 2 | Holiday | Spring Break (University Open, No Classes)
|  | 2017-03-15 | 3 | Holiday | Spring Break (University Open, No Classes)
|  | 2017-03-16 | 4 | Holiday | Spring Break (University Open, No Classes)
|  | 2017-03-17 | 5 | Holiday | Spring Break (University Open, No Classes)
| 11 | 2017-03-20 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-21 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-22 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-23 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-24 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
6 | 12 | 2017-03-27 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-28 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-29 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-30 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-03-31 | 5 | Holiday | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 13 | 2017-04-03 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-04-04 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-04-05 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-04-06 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2017-04-07 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
7 | 14 | 2017-04-10 | 1 | In Person/Online | Wrapping up. Make sure your product owner is happy with the final release. You need to create a slide presentation (one per team). (See the guideline)
|  | 2017-04-11 | 2 | In Person/Online | You need to create an individual poster.
|  | 2017-04-12 | 3 | In Person/Online | You need to create your final document (one per team).
|  | 2017-04-13 | 4 | In Person/Online | Daily Scrum; Double check poster, presentation and final document together.
|  | 2017-04-14 | 5 | In Person/Online | Daily Scrum; Double check poster, presentation and final document together. Double check with me.
| 15 | 2017-04-17 | 6 | Poster Due | On Monday, you need to submit your individual poster. The posters are due by 5 pm on Monday. Submit your poster using the link provided to you under Deliverables section in your Moodle course. We will print them and we bring them to the showcase with easels.
|  | 2017-04-18 | 7 | In Person/Online | On Tuesday, you need to have your final document in the google drive. (one per team) (due by 5 pm)
|  | 2017-04-19 | 8 | In Person/Online | On Wednesday, you need to upload your final slide presentation in the google drive. (due by 5 pm)
|  | 2017-04-20 | 9 | In Person/Online | On Thursday, Each team needs to print one copy of the final document for the showcase.
|  | 2017-04-21 | 10 | Sowcase | On Friday (4pm-9.30 pm) - 3.50pm : Students need to be in ECS - 4:00pm-4:30pm: Group photo on ECS stairs - 4:30pm-5:00pm: Students need to be in PG6-105 for Surveys. - 5:00pm-6:00pm: Students need to help to move chairs from 116 to 122 and then prepare their stations in PG6-116 - 6:00pm: Welcome speech in PG6 lobby. - 6:00pm-9pm: Showcase in PG6 116. (Refreshments will be served after 6.30 pm) - 9pm-9.30pm: Students MUST help to move posters back to ECS and chairs from 112 to 116
8 | 16 | 2017-04-24 | 1 | In Person/Online | On Monday, you need to develop the Introductory Video (teamwork). The videos are due by 5 pm. You need to upload it into the senior project YouTube channel. (See the gudileine) (You need to create a playlist and this video will be the first video of your playlist)
|  | 2017-04-25 | 2 | In Person/Online | On Tuesday, you need to develop the Tutorial Video for Each Actor of Your System (one video per actor) (teamwork). The videos are due by 5 pm. Only VIP students: You need to submit your research paper (or technical note) in the moodle by 5 pm.
|  | 2017-04-26 | 3 | In Person/Online | On Wednesday, you need to develop the Installation & Maintenance Video (teamwork). The videos are due by 5 pm.
|  | 2017-04-27 | 4 | In Person/Online | On Thursday, you need to develop the Shortcomings & Wishlist Video (teamwork). The videos are due by 5 pm.
|  | 2017-04-28 | 5 | Final Deliverables Due | On Friday, you need to push the deliverables on github based on the guidline. You must download a Zip file from your most updated GitHub repository. Upload your zip file using the link provided to you under Deliverables section in your Moodle course. The Final Deliverable is due by 5 pm . Also, one person from each project needs to upload the team's project to seniorproject.cis.fiu.edu. Please find the guidline here: https://webs.cs.fiu.edu/blog/add-new-senior-project/
Formulas:
Date = [Date, row above]+1